## Logframe
PROJECT NAME | Information, Counselling and Legal Assistance for the protection of Palestinians affected by or at risk of displacement
IMPACT | Impact Indicator 1 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
Reduced poverty & vulnerability of Palestinians in the OPTs and the region. | Depth of poverty: Poverty gap index | Planned
Achieved
Source
| Impact Indicator 2 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
| Number of demolitions (tbc) | Planned
Achieved
Source
OCHA?
OUTCOME | Outcome Indicator 1 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014 | Assumptions
Palestinians at risk of displacement within the oPt are better able to uphold their housing land and property rights through provision of legal aid services and increased access to justice . | % of households in Area C and East Jerusalem who receive a temporary suspension of demolition order due to legal representation provided through NRC | Planned | 95% | 95% |  | 95%
Achieved
Source
NRC annual report
| Outcome Indicator 2 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
| % of beneficiaries participating in information sessions who report the information presented will assist them in their daily lives (sex disaggregated) | Planned | tbc |  |  | at least 50%
Achieved
Source
Beneficiary surveys carried out after every information service,NRC annual report
| Outcome Indicator 3 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
| Number of cases of positive action taken as a result of information received from NRC in an effort to reduce forced displacement (weighted measure) | Planned
Achieved
Source
Collated from regular reporting and feedback, NRC annual report
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014 | Assumption
Emergency Legal Response - Provision of emergency legal counselling to Palestinians at risk of displacement in Area C, East Jerusalem and Gaza. | Number of households receiving legal counselling on HLP issues | Planned
Achieved
Source
NRC Annual Report
| Output Indicator 1.2 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
| Number of opened and ongoing cases of legal assistance | Planned
Achieved
Source
NRC Annual Report
| Output Indicator 1.3 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
| Percentage of beneficiaries who are at least satisfied with quality of services provided | Planned
Achieved
Source
NRC Annual Report using beneficiary surveys of households using legal services
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
30% | Number of Palestinians who receive legal services following potential HLP violations in the Gaza Access Restricted Area | Planned | 0
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | NRC Annual Report |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014 | Assumptions
Preventative Legal Response A longer term legal strategy that helps to prevent demolitions and displacement | Number of discriminatory laws, policies or practices exposed through public interest cases | Planned
Achieved
Source
NRC Annual report
| Output Indicator 2.2 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
| Number of lawyers receiving training (sex disaggregated) | Planned
Achieved
Source
NRC Annual report
| Output Indicator 2.3 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
| Number of cases where lawyers have demonstrated usage of information received from NRC training | Planned
Achieved
Source
Surveys conducted after training, NRC Annual report
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
30% | Number of persons receiving information services (disaggregated by gender) | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014 | Assumptions
Policy Change Response -Influencing policy change on HLP violations through advocacy. | Number of advocacy briefings given on specific HLP issues (verbal or written) | Planned
Achieved
Source
NRC Annual Report
| Output Indicator 3.2 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
| Number of instances reported where NRC research documents have been used | Planned
Achieved
Source
Follow up surveys conducted, NRC Annual Report
| Output Indicator 3.3 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 3.4 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
30% |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014 | Assumptions
PA Capacity Building Response - Strengthen the capacity of the PA to provide legal aid in HLP cases. | Extent to which an options paper is produced and being implemented (Scale 1 to 5 see separate note) | Planned | 0 | 3 |  | 4
Achieved
Source
NRC Annual Report quality assured by DFID
| Output Indicator 4.2 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
| Number of direct issues of cooperation where NRC is actively working with UNDP and PA on development of a sustainable legal aid system for HLP law | Planned
Achieved
Source
NRC Annual Report
| Output Indicator 4.3 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 4.4 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
10% |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014 | Assumptions
Planned
Achieved
Source
| Output Indicator 5.2 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
Planned
Achieved
Source
| Output Indicator 5.3 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 5.4 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2014
Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)

## Simple Diagram
Information, Counselling and Legal Assistance for the protection of Palestinians affected by or at risk of displacement
OUTPUTS |  |  | OUTCOME | IMPACT
1 | Emergency Legal Response - Provision of emergency legal counselling to Palestinians at risk of displacement in Area C, East Jerusalem and Gaza. | 30% | Palestinians at risk of displacement within the oPt are better able to uphold their housing land and property rights through provision of legal aid services and increased access to justice . | Reduced poverty & vulnerability of Palestinians in the OPTs and the region.
2 | Preventative Legal Response A longer term legal strategy that helps to prevent demolitions and displacement | 30%
3 | Policy Change Response -Influencing policy change on HLP violations through advocacy. | 30%
4 | PA Capacity Building Response - Strengthen the capacity of the PA to provide legal aid in HLP cases. | 10%
5 | 0 | 0%

## Diagram
Information, Counselling and Legal Assistance for the protection of Palestinians affected by or at risk of displacement
Results Chain |  |  | Indicators | Baseline 2012 | Target 2014 | Source
IMPACT | Reduced poverty & vulnerability of Palestinians in the OPTs and the region. |  | Depth of poverty: Poverty gap index | 0 | 0 | 0
|  |  | Annual number of demolitions | 0 | 0 | OCHA?
OUTCOME | Palestinians at risk of displacement within the oPt are better able to uphold their housing land and property rights through provision of legal aid services and increased access to justice . |  | % of households in Area C and East Jerusalem who receive a temporary suspension of demolition order due to legal representation provided through NRC | 95% | 95% | NRC annual report
|  |  | % of beneficiaries participating in information sessions who report the information presented will assist them in their daily lives (sex disaggregated) | tbc | at least 50% | Beneficiary surveys carried out after every information service,NRC annual report
|  |  | Number of cases of positive action taken as a result of information received from NRC in an effort to reduce forced displacement (weighted measure) | 0 | 0 | Collated from regular reporting and feedback, NRC annual report
OUTPUTS | Emergency Legal Response - Provision of emergency legal counselling to Palestinians at risk of displacement in Area C, East Jerusalem and Gaza. | 30% | Number of households receiving legal counselling on HLP issues | 0 | 0 | NRC Annual Report
|  |  | Number of opened and ongoing cases of legal assistance | 0 | 0 | NRC Annual Report
|  |  | Percentage of beneficiaries who are at least satisfied with quality of services provided | 0 | 0 | NRC Annual Report using beneficiary surveys of households using legal services
|  |  | Number of Palestinians who receive legal services following potential HLP violations in the Gaza Access Restricted Area | 0 | 0 | NRC Annual Report
| Preventative Legal Response A longer term legal strategy that helps to prevent demolitions and displacement | 30% | Number of discriminatory laws, policies or practices exposed through public interest cases | 0 | 0 | NRC Annual report
|  |  | Number of lawyers receiving training (sex disaggregated) | 0 | 0 | NRC Annual report
|  |  | Number of cases where lawyers have demonstrated usage of information received from NRC training | 0 | 0 | Surveys conducted after training, NRC Annual report
|  |  | Number of persons receiving information services (disaggregated by gender) | 0 | 0 | 0
| Policy Change Response -Influencing policy change on HLP violations through advocacy. | 30% | Number of advocacy briefings given on specific HLP issues (verbal or written) | 0 | 0 | NRC Annual Report
|  |  | Number of instances reported where NRC research documents have been used | 0 | 0 | Follow up surveys conducted, NRC Annual Report
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
| PA Capacity Building Response - Strengthen the capacity of the PA to provide legal aid in HLP cases. | 10% | Extent to which an options paper is produced and being implemented (Scale 1 to 5 see separate note) | 0 | 4 | NRC Annual Report quality assured by DFID
|  |  | Number of direct issues of cooperation where NRC is actively working with UNDP and PA on development of a sustainable legal aid system for HLP law | 0 | 0 | NRC Annual Report
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
| 0 | 0% | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0

## Annual Review
Information, Counselling and Legal Assistance for the protection of Palestinians affected by or at risk of displacement
Results Chain |  |  | Indicators | Planned | Achieved | Score |  | Risk | Planned | Achieved | Score |  | Risk | Planned | Achieved | Score |  | Risk
|  |  |  | 2013 |  | 2013 |  | 2013 | 2014 |  | 2014 |  | 2014 | Target 2014 |  | 2014 |  | 2014
IMPACT | Reduced poverty & vulnerability of Palestinians in the OPTs and the region. |  | Depth of poverty: Poverty gap index | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | Number of demolitions (tbc) | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
OUTCOME | Palestinians at risk of displacement within the oPt are better able to uphold their housing land and property rights through provision of legal aid services and increased access to justice . |  | % of households in Area C and East Jerusalem who receive a temporary suspension of demolition order due to legal representation provided through NRC | 95% | 0% | n/a |  |  | 0 | 0 | n/a |  |  | 0.95 | 0 | n/a
|  |  | % of beneficiaries participating in information sessions who report the information presented will assist them in their daily lives (sex disaggregated) | 0 | 0 |  |  |  | 0 | 0 |  |  |  | at least 50% | 0
|  |  | Number of cases of positive action taken as a result of information received from NRC in an effort to reduce forced displacement (weighted measure) | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
OUTPUTS | Emergency Legal Response - Provision of emergency legal counselling to Palestinians at risk of displacement in Area C, East Jerusalem and Gaza. | 30% | Number of households receiving legal counselling on HLP issues | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | Number of opened and ongoing cases of legal assistance | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | Percentage of beneficiaries who are at least satisfied with quality of services provided | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | Number of Palestinians who receive legal services following potential HLP violations in the Gaza Access Restricted Area | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Preventative Legal Response A longer term legal strategy that helps to prevent demolitions and displacement | 30% | Number of discriminatory laws, policies or practices exposed through public interest cases | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | Number of lawyers receiving training (sex disaggregated) | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | Number of cases where lawyers have demonstrated usage of information received from NRC training | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | Number of persons receiving information services (disaggregated by gender) | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Policy Change Response -Influencing policy change on HLP violations through advocacy. | 30% | Number of advocacy briefings given on specific HLP issues (verbal or written) | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | Number of instances reported where NRC research documents have been used | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| PA Capacity Building Response - Strengthen the capacity of the PA to provide legal aid in HLP cases. | 10% | Extent to which an options paper is produced and being implemented (Scale 1 to 5 see separate note) | 3 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 4 | 0 | n/a | 0%
|  |  | Number of direct issues of cooperation where NRC is actively working with UNDP and PA on development of a sustainable legal aid system for HLP law | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| 0 | 0% | 0 | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
OVERALL OUTPUT SCORE |  | 100% |  |  |  | n/a | 0% |  |  |  | 0 | 0% |  |  |  | 0 | 0%
| Value | Threshold
A++ | 150% | 137.5% | Outputs substantially exceeded expectation
A+ | 125% | 112.5% | Outputs moderately exceeded expectation
A | 100% | 87.5% | Outputs met expectation
B | 75% | 62.5% | Outputs moderately did not meet expectations
C | 50% |  | Outputs substantially did not meet expectations
n/a | 0%
Risk
Low | 1
Medium | 2
High | 3

## Output_4.1 methodology
Extent to which options paper has been produced
1 | 2 | 3 | 4 | 5
Options paper not produced | Options paper produced but not comprehensive and no costings | Options paper produced with recommendations and some costings | Options paper produced with clear recommendations and costings and incorporated into PA's planning | Options paper produced with clear recommendations and costings and incorporated into PA's planning